## Sheet1
Business Continuity Planning COVID-19
Not Started | Underway | Complete | Planning Activities |  | Action | Comment
|  |  | 1.1 | Assign responsibility for planning and preparedness to a senior executive and a deputy
|  |  | 1.2 | Obtain information on COVID-19
|  |  | 1.3 | Consult within the company, with workers and worker representatives
|  |  | 1.4 | Consult with suppliers on measures they are taking and on potential disruptions to supply chains
|  |  | 1.5 | Assess ‘high level’ impact on your business and attach appropriate priority to the planning process 1.6 Develop a business continuity plan
|  |  | 1.7 | Establish authorities, triggers and procedures for implementing plan
|  |  | 1.8 | Test the plan in exercises
|  |  | 1.9 | hare best practice with other businesses
|  |  | 1.1 | Revisit plan periodically
Business Issues to Address
|  |  | 2.1 | Identify critical activities and the employees and inputs required to maintain them
|  |  | 2.2 | Consider the possible impact of employee absences
|  |  | 2.3 | Consider the possible impact of disruption to the supply of inputs from suppliers in Ireland and overseas suppliers
|  |  | 2.4 | Examine the likely impact of COVID-19 on your market and on your customers’ requirements
|  |  | 2.5 | Identify and agree strategic imperatives
|  |  | 2.6 | Understand the business need for face-to-face meetings should there be community transmission of COVID-19 with a risk of person to person spread. Consider the potential for remote working.
|  |  | 2.7 | Establish authorities, triggers and procedures for implementing plan.
|  |  | 2.8 | Consider the issues for business related travel due to COVID-19
|  |  | 2.9 | Consider the financial management implications due to COVID-19
|  |  | 2.1 | Examine the extent to which others will be dependent on your business due to COVID19
|  |  | 2.11 | Consider the circumstances under which you might decide to scale back or suspend operations due to COVID-19
Measures to Underpin Continuity
|  |  | 3.1 | Nominate deputies
|  |  | 3.2 | Cross-train, and identify alternative sources of labour
|  |  | 3.3 | Communicate with staff in a manner appropriate to the current state of COVID-19 phase as guided by national recommendations
|  |  | 3.4 | Prepare emergency communications plan
|  |  | 3.5 | Plan for increased take-up of employee welfare services
|  |  | 3.6 | Prepare policies on sick leave and compassionate leave due to COVID-19
|  |  | 3.7 | Prepare policies on foreign travel during COVID19 event
|  |  | 3.8 | Plan for the needs of staff overseas
|  |  | 3.9 | Make arrangements to assure supplies during the COVID-19 event
|  |  | 3.1 | Consider the possibility of changes to your product, your service, or your interaction with customers, due to COVID-19, and plan for any changes you consider appropriate
|  |  | 3.11 | Review insurance coverage